SGP APPLICATION FORM

(to be translated into national Language)

All questions must be answered or the proposal will not be considered for funding.

If the space provided is not sufficient please attached a separate piece of paper for each question. Do not answer the questions in one large essay.

English or the national language is equally acceptable.

| - Title of Project - Tumen River Green Pilgrimage Project (Local people centered environmental monitoring program in Tumen River Area) |  |  |
| --- | --- | --- |
| - Exact Location - The Tumen River area, including adjoining river areas of the Democratic People's Republic Of Korea (DPRK) and the People's Republic of China. The location stretches from the lower reaches of Tumen Fangchuan to the Changbai Mountain. Program Implementation Route Region Ⅰ Kaishantun→Shanhe Region Ⅱ Shanhe→Fuyu→Baijin→Dehua (Nanping) Region Ⅲ Dehua→Luguo→Chongshan Region Ⅳ Chongshan→Changbai Mountain Region Ⅴ Lower reaches of Tumen Fangchuan→Quanhe port Region Ⅵ Quanhe port→Jingxin→Hunchun city→Mijiang→Liangshui Region Ⅶ Liangshui→Tumen river Region Ⅷ Tumen river→Yueqing→Kaishantun |  |  |
| - Implementing Agent - Green Korea United(Republic of Korea) - Green Yanji (China) |  |  |
| - Duration of Project - 1 year |  |  |
| - Does the project have any connection with other projects that are funded by national Or international NGOs, bilateral donors, UNDP, GEF, WB, ADB or by your national Government. If so, please provide details - Bilateral donor, AVEDA corporation will provide a portion of their sales in support of the Green Pilgrimage. The donations will provide the financial support needed for Green Korea staff to travel to the Tumen River areas as well as awareness raising program cost in South Korea. (Ex. Homepage about Tumen River Green Pilgrimage) |  |  |
| - Amount request under Small Grants Program - $5,000 |  |  |
| - Bank Account Details i) Name of Account 녹색연합 생태공동체팀(Green Korea United) ii) Number of Account 325-01-167914 - Name and Address of Bank JHOHUNG BANK,(Younji Branch ) Korea Ecumenical Build. Yonjidong 136-56, jongrogu, Seoul |  |  |
| - Please provide summary of proposal objectives This program includes several fieldtrips. The fieldtrips’ main focus is to: - Monitor local environmental situations - Promote active, productive discussions with local people - Raise environmental awareness both in the region, and throughout South Korea - Solve the environmental problems in the targeted area with the help of local people Furthermore this program will promote a peaceful reconciliation process between the two Koreas by focusing on a common area of interest such as the Tumen River area. |  |  |
| - How will these objectives be achieved? ##### Our pilgrimage program has two main actors including Green Yanji and the local people in the Tumen River area. Green Yanji is a very important local environmental organization, which has very diverse connections among experts, youth groups and local people. The participation of local people is crucial to ensure protection of the area. With Green Yanji’s active participation in this program especially, the local people will be very apt to join the campaign. ##### In this program, we will meet with the local people to open discussions and inform them ##### Of the problems. By joining the pilgrimage, locals will experience first hand the degree ##### to which their homelands have been deteriorated. This awakening about the ##### Environmental Problems will eventually lead local people to become active participants ##### in environmental problem solving. ##### Green Korea United and Green Yanji will assist the local people of the region by providing human and other resources whenever they are needed. |  |  |
| - Describe how the target population will benefit from the project and link those Benefits to the project activities. - After we accomplish our pilgrimage, local people will have a different idea about the development of their region. With the recent attention of The Tumen River Region Development, people have focused on considering only economic development. Luckily, this pilgrimage will provide an alternative to the proposed development that can offer ecological protection. Our pilgrimage will provide many opportunities for local people to discuss their development problems very sincerely and to contact active Environmental groups that will assist them continuously. |  |  |
| - Comment on gender equity in formulation, design and implementation of this project. Does it assist any disadvantaged groups / people? - Green Korea United, and Green Yanji encourage the support of women and minority Groups. Furthermore the main implementer of this program is a female environmental Activist. We will promote the participation of the disadvantaged people. Even though Green Pilgrimage is very physical work, the participation of the disadvantaged people is very Important to us. |  |  |
| - Describe the impact your project has on improving the environment, in particular On biodiversity and waters protection - The Tumen River is an international waterway with a growing reputation as an ecologically important area in the region. However, the discharging of industrial and domestic pollutants into the Tumen River have deteriorated its reputation by causing serious environmental problems. To get its reputation back, the affected area requires regional cooperation as well as assistance from international NGOs. Therefore, raising people's awareness of the environmental issues in this area is critical to successfully improve its condition. The Green Pilgrimage program is a very appropriate program to obtain this goal. GKU has successfully implemented The Green Pilgrimage program for three consecutive years, beginning in 1998. We have walked the areas where mega-development projects have been underway. Throughout our pilgrimages, we could inform and raise awareness about the environmental problems using the mass-media’s focus. Furthermore, local residents have actively participated in our programs. This is a result of the pilgrimage’s success in forming strong bonds between NGOs and the local people. Currently, people in those areas are actively joining in environmental protection activities in their areas. We believe that the program in Tumen river area will have the same positive outcome. We can make a strong connection with the local people through this pilgrimage. Eventually, they will be educated and get the environmental sensibility to protect their Area’s Biodiversity and water quality. Through this program we can make a Tumen River pollution watching network Centered around local people. This will further develop the long-term goal of Empowering the local people to monitor and control their respective areas. |  |  |
| 13. Please complete the schedule below, showing key activities, dates, and who will be responsible for implementing the activities under your project |  |  |
| Activity Implementation date Person in Charge |  |  |
| 2001 Tumen River Green Pilgrimage |  |  |
| Preparatory Pilgrimage | 8, June – 12, June (5 days and 4 nights) 5 people | Lee, Qiang (Green Yanji) Lee, Yujin (Green Korea) |
| Pilgrimage Region Ⅰ Kaishantun→Shanhe | 18, June – 26, June (9 days and 8 nights) 10 people - Local people - Experts - Green Yanji - Green Korea - Volunteer | Mr. Jiang Long (Green Yanji) |
| Pilgrimage Region Ⅱ Shanhe→Fuyu→Baijin→Dehua (Nanping); |  |  |
| Pilgrimage Region Ⅲ Dehua→Luguo→Chongshan; |  |  |
| Pilgrimage Region Ⅳ Chongshan→Changbai Mountain |  |  |
| Pollution Monitoring Analysis by the local people | 26, June – 30, September | Mr. Li Qiang (Green Yanji) |
| Organizing local people to participate in the environmental activities | 26, June – 30, September | Mr. Li Qiang (Green Yanji) |
| Reporting the 2001 Green Pilgrimage (first project) | 30, September 2001 | Ms Lee, Yujin (Green Korea) |
| Evaluation of the first project | 30, November 2001 | UNDP |
| 2002 Tumen River Green Pilgrimage |  |  |
| Preparatory Pilgrimage | 5, April – 8, April (4 days and 3 nights) 5 people | Mr. Lee, Qiang(Green Yanji) Ms Lee, Yujin(Green Korea) |
| Pilgrimage Region Ⅴ Lower reaches of Tumen Fangchuan→Quanhe port | 12, April – 19, April (8 days and 7 nights) 10 people - Local people - Experts - Green Yanji - Green Korea - Volunteer | Mr. Jiang Long (Green Yanji) |
| Pilgrimage Region Ⅵ Quanhe port→Jingxin→Hunchun city →Mijiang→Liangshu |  |  |
| Pilgrimage Region Ⅶ Liangshui→Tumen river |  |  |
| Pilgrimage Region Ⅷ Tumen river→Yueqing→Kaishantun; |  |  |
| Reporting the 2002 Green Pilgrimage (second project) | 1, May, 2002 | Ms Lee, Yujin Green Korea |
| Evaluation of the second project | 31, July, 2002 | UNDP |
| 14. Please provide evidence of self-help and demonstrate the commitment of local people / authorities to this project. - Green Yanji, co-partner of Green Korea United, has 350 members and 3 sub-chapters That can organize the meetings with local people in every area. Their members, who are locals themselves, will actively participate to prepare this pilgrimage. These 350 civilians will be main seeds to proliferate the “green ideas” in this region through pilgrimage. |  |  |
| 15. How to do propose to sustain the project once all project funds have been expended? Eg, how will you meet maintenance, repair, and ongoing operational costs for the project? Please provide a letter of support from pertinent authorities - Green Korea United and Green Yanji will absorb any additional costs that are incurred From implementation of this project. |  |  |

# GEF FUNDS

- Please list item by item (including quantities to be purchased) the proposed budget for the use of the GEF funds

| # ITEM | # SPECIFICATIONS | # QUANTITY | # UNIT PRICE | # TOTAL |
| --- | --- | --- | --- | --- |
| Tumen River Green Pilgrimage(2001-2002) |  |  |  |  |
| Accommodation(2001) | Preparatory Pilgrimage Pilgrimage | 5people 4nights 10people 8nights | Per night Per person 3$ | 5*4*3=60$ 10*8*3=240$ Total =300$ |
| Accommodation(2002) | Preparatory Pilgrimage Pilgrimage | 5people 3nights 10people 7nights | Per night Per person 3$ | 5*3*3=45$ 10*7*3=210$ Total =255$ |
| Food(2001) | Preparatory Pilgrimage Pilgrimage | 5people 3times 5days 10people 3times 9days | Each time Per person 2$ | 5*3*5*2=150$ 10*3*9*2=540$ Total =690$ |
| Food(2002) | Preparatory Pilgrimage Pilgrimage | 5people 3times 4days 10people 3times 8days | Each time Per person 2$ | 5*3*4*2=120$ 10*3*8*2=480 Total =600$ |
| Education material | Green Pilgrimage Education material for South Korea | 100 | 2$ | 200$ |
| Transportation | Public Transportation | (2 times-2001, 2002) | Each Time 500$ | 1,000$ |
| Materials | Pollution gage equipment (Water pollution) | 5 | 100$ | 500$ |
|  | Video tape | 10 | 10$ | 100$ |
|  | Edit Video tape | (2 times-2001, 2002) | 200$ | 400$ |
|  | T- Shirts | 50 | 8$ | 400$ |
|  | Banner and Flags | 2 | 10$ | 20$ |
|  | Green Pilgrimage Education materials | 100 | 3$ | 300$ |
|  | Film & Development |  |  | 235$ |
| # TOTAL BUDGET EXPENDITURE IS 5,000 $ |  |  |  |  |

Note: In regard to UNDP Small grant program’s non-preferred expenditure items: project support; monitoring cost; brochures.  The pilgrimage’s main purpose is centered around the experiences of local people in the Tumen River area. To properly disseminate understanding of the environmental situation in this area, it is essential to create some supplemental materials. Furthermore, success of the project is contingent on the establishment of local monitoring networks. Creating such networks will require the initial help of some non-local participants. Therefor, it is imperative that the project address costs in these respective categories.

Counterpart Funds

17.  Please provide details of the contributions (cash or in kind) that will make available to the project

| # ITEM | ## SOURCE OF FUNDS | QUANTITY | UNIT PRICE | # TOTAL |
| --- | --- | --- | --- | --- |
| Salary For the Staff | Green Korea | 14 months | 200$ | 2,800$ |
| Travel(Air Ticket) for the Staff Travel(Air Ticket) for the volunteer | AVEDA Volunteer | 2 times(2 people) (5people) | 500$ | 2,000$ 2,500$ |
| Translation | AVEDA | 5 times | 300$ | 1,500$ |
| Building | Green Korea Green Yanji (in China) |  |  |  |
| Equipment | Green Korea Green Yanji (in China) |  |  |  |
| ### TOTAL BUDGET EXPENDITURE IS 8,800$ |  |  |  |  |

### TO BE COMPLETED BY THE National SGP Manager

- Please indicate how it is intended to disburse funds, monitor activities and report on progress